## Sheet1
No. | Program Code | Program Name | Status | Programmer | Finish Date | Remark
1 | GM020 | Company Master | Completed | Nova | 2012-12-03
2 | GM030 | Branch Master | Completed | Nova | 2012-12-04
3 | IM010 | Material Master | Completed | Nova | 2012-12-05
4 | IM030 | Material Group | Completed | Nova | 2012-12-06
5 | IM050 | Warehouse Master | Completed | Nova | 2012-12-06
6 | IM060 | Location Master | Completed | Nova | 2012-12-07
7 | IT010 | Transfer Request | Completed | Nova | 2012-12-10
8 | IT020 | Transfer Out | Completed | Nova | 2012-12-11
9 | IT030 | Transfer In | Completed | Nova | 2012-12-12
10 | IT040 | Inventory Adjustment | Completed | Nova | 2012-12-13
11 | IT050 | Stock Taking | Completed | Nova | 2012-12-14
12 | IT060 | Stock Taking Process | Completed | Nova | 2012-12-17
13 | PM010 | Vendor Master | Completed | Nova | 2012-12-19
14 | PM020 | Vendor Type | Completed | Nova | 2012-12-19
15 | PT010 | Purchase Request | Completed | Winston | 2012-12-11
16 | PT020 | Quotation Request | Completed | Winston | 2012-12-12
17 | PT030 | Purchase Order | Completed | Winston | 2012-12-13
18 | PT040 | Purchase Receipt | Completed | Winston | 2012-12-18
19 | PT050 | Purchase Return | Completed | Winston | 2012-12-19
20 | SM010 | Buyer Master | Completed | Winston | 2012-12-19
21 | ST010 | Sales Order | On Progress | Winston
22 | ST020 | Sales Price | On Progress | Nova